## RTM
Requirements traceability matrix
Type in the white cells. The grey cells have formulas: do not type in them. Replace the four example rows with your own requirements.
Requirements
With one test case or more
With no test case (gaps)
Coverage
Last result failed
Requirement ID | Requirement | Source | Priority | Test case IDs | Test cases linked | Last result | Last run date | Defects | Coverage status | Owner | Notes
REQ-101 | A registered user can sign in with email and password | JIRA SHOP-12 | High | TC-12, TC-13 |  | Passed | 2026-09-28 |  |  | Maria
REQ-102 | A user can reset a forgotten password by email | JIRA SHOP-15 | High | TC-14 |  | Failed | 2026-09-28 | BUG-207 |  | Maria | Reset link expires too early
REQ-103 | The cart keeps its items after the user signs out and in again | JIRA SHOP-21 | Medium | TC-20, TC-21, TC-22 |  | Not run |  |  |  | Ken | Planned for the next test run
REQ-104 | An order confirmation email goes out after payment | Spec 4.2 | Medium | [6 empty] | Ken | No test case yet: this is a coverage gap

## How to use
How to use this template
1. Write one row for each requirement. Give each requirement an ID.
2. In 'Test case IDs', type the IDs of the test cases that verify the requirement. Put a comma between two IDs.
3. After each test run, set 'Last result' to Passed, Failed, or Not run, and type the date.
4. Type the ID of each defect that a failed test found.
5. Read the summary at the top. A requirement with no test case is a coverage gap.
Three types of traceability
Forward: from a requirement to its test cases. It shows that each requirement is tested.
Backward: from a test case to its requirement. It shows that no test is out of scope.
Bidirectional: both directions in one matrix. This template is bidirectional when each test case ID is in one row or more.
When a spreadsheet is not enough
You update this sheet by hand after each test run. TestCollab builds the same matrix from your requirements in Jira, GitLab, or Azure DevOps, and updates it after each test run.
https://testcollab.com/features/requirements-traceability-matrix